## Slide 1
FOUNDER WORKBOOK
Startup Operations & Launch Plan
LearnReach's working plan for customer acquisition, service delivery, financial validation and launch readiness.
Planning document aligned with the LearnReach MVP demo. Assumptions are labelled for validation; confirm financial and legal details before committing.
LearnReach
23 October 2026

## Slide 2
GETTING STARTED
How To Use This Template
Fill in every dashed box
Dashed, italic gray text marks a field to replace. Click it, delete the prompt, and type your own answer directly on the slide.
Follow the section order
Three sections — GTM & Marketing, Operations, and Legal Structure — each open with a divider slide. Work through them in order or jump to what you need.
Keep answers specific
Write real names, numbers, and dates — not generic statements. A specific, half-finished plan beats a polished, vague one.
Duplicate cards as needed
Need a 4th SOP or a 3rd contract? Right-click a card or row in PowerPoint's slide/outline view and duplicate it, then edit the copy.
FOUNDER WORKBOOK · Startup Operations & Launch Plan
2

## Slide 3
SECTION 1
Sales & Marketing Strategy
Define who you're selling to, how you'll reach them, and how they'll buy.
FOUNDER WORKBOOK · STARTUP OPERATIONS & LAUNCH PLAN

## Slide 4
SECTION 1 · Sales & Marketing
Brand Identity
State your brand mission, personality, voice, and visual direction in one place.
BRAND MISSION (ONE SENTENCE)
We help educational businesses reach more students through clear, focused digital marketing.
BRAND PERSONALITY (3–5 ADJECTIVES)
Clear · Helpful · Practical · Trustworthy · Student-focused
BRAND VOICE
Friendly, professional and encouraging. Use simple language, practical advice and honest claims.
VISUAL DIRECTION
Blue and white palette; clean typography; education-focused imagery; simple layouts and clear calls to action.
FOUNDER WORKBOOK · Section 1: GTM & Marketing Strategy
4

## Slide 5
SECTION 1 · Sales & Marketing
Sales Funnel
Describe each stage for your venture, then flag where customers drop off — and your fix.
1. Awareness
Personalised email/WhatsApp outreach, LinkedIn, referrals and the LearnReach website.
→
2. Interest
Clear services: digital advertising, social media marketing, content creation and enrollment campaigns.
→
3. Decision
Discovery call, clear campaign scope, expected deliverables, timeline and transparent price proposal.
→
4. Action
Agree scope and price, sign service agreement, pay agreed invoice, then complete onboarding.
LIKELY DROP-OFF TO TEST: Interest → Decision. Prospects may like the idea but hesitate to pay before seeing evidence. FIX: conduct discovery calls, define a small pilot with clear deliverables, and collect feedback before offering a monthly package.
FOUNDER WORKBOOK · Section 1: GTM & Marketing Strategy
7

## Slide 6
SECTION 1 · Sales & Marketing
Channel Selection
Choose 1–2 channels to test first. Duplicate the card below if testing a second.
CHANNEL 1
CHANNEL NAME
Direct, personalised email and WhatsApp outreach
TARGET AUDIENCE IT REACHES
Independent course creators and small training providers in Rwanda
CONTENT / APPROACH + SUCCESS METRIC
Contact 30 prospects; aim for 10 interviews in 30 days. Track replies, calls, proposals and paid pilots.
CHANNEL 2 (optional)
CHANNEL NAME
LearnReach website + LinkedIn / educator referrals
TARGET AUDIENCE IT REACHES
Tutors, training centres and course creators who need more student enquiries
CONTENT / APPROACH + SUCCESS METRIC
Show the four service areas and invite visitors to use the contact form. Track qualified enquiries and calls booked.
FOUNDER WORKBOOK · Section 1: GTM & Marketing Strategy
8

## Slide 7
SECTION 2
Financial Model
This section builds your financial foundation. Draw on your pricing strategy, revenue projections, cash flow tracker, and burn rate calculations from the module.
FOUNDER WORKBOOK · STARTUP OPERATIONS & LAUNCH PLAN

## Slide 8
SECTION 4 · FINANCIAL
Pricing Strategy
State which pricing approach you're using and why it's the right fit for your venture — then justify your price point in terms of customer value.
Cost-Plus
Competitor-Based
Value-Based
Working hypothesis: VALUE-BASED pricing (test with customers before finalising).
WHY THIS APPROACH FITS YOUR VENTURE
A value-based approach connects the fee to campaign scope and the value of clearer promotion, organised enquiries and reporting. Validate willingness to pay during interviews and pilots.
YOUR PRICE POINT(S)
Working price hypothesis: RWF 150,000 per month for a clearly defined support package.
VALUE JUSTIFICATION
The package should deliver agreed campaign tasks, useful reporting and reliable follow-up. Confirm deliverables, time and customer willingness to pay before treating this as a final price.
FOUNDER WORKBOOK · Section 4: Financial Model
19

## Slide 9
SECTION 4 · FINANCIAL
Revenue Projections
Use the Bottom-Up method — show your realistic reach, conversion rate, units sold, and resulting revenue for at least Months 1, 3, and 6.
THE FORMULA: Revenue = Realistic Reach × Conversion Rate × Price per Unit. Every number should be one you can defend, not one that sounds good.
MONTH
REALISTIC REACH
CONVERSION RATE
UNITS SOLD
PRICE / UNIT
REVENUE
Month 1
30 prospects
0% paid
0 clients
RWF 150k
RWF 0
Month 3
60 prospects
3.3%
2 clients
RWF 150k
RWF 300k
Month 6
90 prospects
3.3%
3 clients
RWF 150k
RWF 450k
FOUNDER WORKBOOK · Section 4: Financial Model
20

## Slide 10
SECTION 4 · FINANCIAL
Cash Flow Tracker
Track what's actually moving in and out of your account each month — cash flow, not revenue, is what keeps a venture alive.
MONTH
CASH IN (Revenue + Other)
CASH OUT (Expenses)
NET CASH FLOW
ENDING BALANCE
Month 1
RWF 0 revenue
Record actual costs
Calculate actual net
Track actual balance
Month 2
Record actual revenue
Record actual expenses
Calculate net cash flow
Update balance
Month 3
Record actual revenue
Record actual expenses
Calculate net cash flow
Update balance
Starting cash balance carries over from the prior month's ending balance — add rows if you're tracking beyond three months.
FOUNDER WORKBOOK · Section 4: Financial Model
21

## Slide 11
SECTION 4 · FINANCIAL
Burn Rate & Runway
Know exactly how many months you have before you need more cash — or more revenue — to keep operating.
BURN RATE = (Starting Cash − Ending Cash) ÷ Number of Months RUNWAY = Cash on Hand ÷ Monthly Burn Rate
CURRENT MONTHLY BURN RATE
To be calculated from actual expenses
CASH ON HAND TODAY
Enter actual available cash
RUNWAY (MONTHS)
Calculate once cash and burn are known
WHAT CHANGES IF REVENUE GROWS SLOWER THAN PLANNED?
If revenue is below plan, pause paid promotion, keep delivery lean, prioritise direct outreach, and review costs before committing to new spending.
FOUNDER WORKBOOK · Section 4: Financial Model
22

## Slide 12
SECTION 3
Operations Plan
Document the systems that let your venture run consistently — without everything going through you. Draws on your SOP work and Weekly Pulse design.
FOUNDER WORKBOOK · STARTUP OPERATIONS & LAUNCH PLAN

## Slide 13
SECTION 3 · OPS
Three Core SOPs — Field Guide
Every SOP on the next slide follows this same five-field structure. Suggested starting points: Customer Onboarding, Customer Support, Financial Keep-the-Lights-On.
SOP Name
What process is this?
Customer Onboarding
Trigger
When is it used — what kicks it off?
New customer completes checkout and makes payment
Step-by-Step Process
The lean, numbered steps — enough that someone new could follow it.
Automated welcome email sends within 5 minutes with login details and a "getting started" checklist. Mark onboarding complete in the tracker once they've used the product 3+ times or hit their first key action
Tools Used
The specific apps/tools involved.
Gmail/Outlook (welcome email), Airtable (onboarding tracker), Zoom/Meet (support call)
Owner
Who is accountable for this running well?
Founder
FOUNDER WORKBOOK · Section 2: Operations Plan
10

## Slide 14
SECTION 3· OPS
Your Three Core SOPs
Fill in one card per SOP. Substitute any process more relevant to your venture.
SOP 1 — Customer Onboarding
TRIGGER
New client accepts proposal and agrees scope
STEP-BY-STEP
1) Confirm goals and audience. 2) Agree deliverables, timeline and fee. 3) Send agreement/invoice. 4) Collect assets and launch brief.
TOOLS
Email, website form, spreadsheet, Google Drive
OWNER
Founder — Ferdinand Hasingizwumukiza
SOP 2 — Customer Support
TRIGGER
Client asks a question or reports a campaign issue
STEP-BY-STEP
1) Acknowledge within one business day. 2) Clarify issue and evidence. 3) Agree action and deadline. 4) Follow up and log outcome.
TOOLS
Email, WhatsApp, campaign tracker
OWNER
Founder — Ferdinand Hasingizwumukiza
SOP 3 — Financial Keep-the-Lights-On
TRIGGER
Weekly review or client payment / expense event
STEP-BY-STEP
1) Record income and costs. 2) Match invoices and receipts. 3) Review cash position and pilot performance.
TOOLS
Spreadsheet, invoices, receipts, bank/mobile-money records
OWNER
Founder — Ferdinand Hasingizwumukiza
FOUNDER WORKBOOK · Section 2: Operations Plan
11

## Slide 15
SECTION 3 · OPS
FOUNDER WORKBOOK · Section 2: Operations Plan
12
The Weekly Pulse
Describe 2–3 operational rituals. For each: when it happens, who attends, what's different vs. today.
Monday Stand-up
WHEN
Monday, 30 minutes
WHO ATTENDS
Founder; invite client only when needed
WHAT'S DIFFERENT
Set weekly priorities, review leads, deadlines and client follow-ups.
Friday Demo / Retro
WHEN
Friday, 30 minutes
WHO ATTENDS
Founder; client joins for campaign review when useful
WHAT'S DIFFERENT
Review outputs, feedback, metrics and lessons; decide next actions.
No-Meeting Zones
WHEN
Reserve two focused work blocks each week
WHO ATTENDS
Founder
WHAT'S DIFFERENT
Protect time for campaign delivery and customer interviews; use meetings only when needed.

## Slide 16
SECTION 3 · OPS
Single Source of Truth
Name your venture's central hub and how you'll enforce Link, Don't Attach.
PLATFORM
Google Drive + a simple lead/campaign tracker spreadsheet.
WHAT LIVES THERE
Client briefs, signed agreements, invoices, content plans, campaign reports, customer feedback and finance records.
ENFORCING "LINK, DON'T ATTACH"
Create one folder per client and keep the master tracker linked from it. Record every enquiry, decision, deadline and deliverable in the tracker. Store documents centrally and share links rather than multiple versions.
FOUNDER WORKBOOK · Section 2: Operations Plan
13

## Slide 17
SECTION 4
Legal Structure Plan
Document the legal foundation of your venture, drawing on business registration and contracts fundamentals.
FOUNDER WORKBOOK · STARTUP OPERATIONS & LAUNCH PLAN

## Slide 18
SECTION 4 · LEGAL
Chosen Structure
Circle or bold your choice below, then explain why it fits your stage.
Sole Proprietorship
Partnership
LLC (Ltd)
Working option to review: Sole Proprietorship (confirm with a qualified local adviser/RDB).
WHY THIS STRUCTURE FITS YOUR RISK LEVEL, CAPITAL PLANS & STAGE
A simple structure may suit an early, founder-led service business, but the final choice should reflect liability, tax, registration requirements and future growth plans in Rwanda.
PERSONAL LIABILITY THIS STRUCTURE CARRIES
Liability depends on the legal form and applicable Rwandan law. Confirm obligations and protections with the relevant authority or a qualified adviser before registering or signing major contracts.
FOUNDER WORKBOOK · Section 3: Legal Structure Plan
15

## Slide 19
SECTION 4 · LEGAL
Registration Roadmap
Outline your registration steps, referencing your local government's official requirements.
1
1. Confirm business name availability and the correct registration route with the Rwanda Development Board (RDB).
→
2
2. Prepare the required founder and business information; confirm current documents and fees with RDB.
→
3
3. Complete the applicable registration process and save official records.
→
4
4. Confirm tax, invoicing and any sector-specific obligations with the relevant Rwandan authorities/adviser.
KEY LOCAL REQUIREMENTS TO REFERENCE
Verify current requirements directly with RDB and relevant tax authorities before acting; this roadmap is a planning checklist, not legal advice.
TARGET REGISTRATION DATE
To be confirmed after checking current requirements
FOUNDER WORKBOOK · Section 3: Legal Structure Plan
16

## Slide 20
SECTION 4 · LEGAL
Contracts You Need
Identify at least two early-stage contracts that apply to your venture right now.
Options: NDA · Employee / Contractor Agreement · Service Agreement · Founder Agreement
CONTRACT
Client Service Agreement
WHY YOU NEED IT NOW
Defines the work, scope, price, payment terms, approvals and what happens if either side needs to stop.
WHAT IT MUST SPECIFICALLY COVER
Deliverables, timeline, fees, revisions, client responsibilities, confidentiality, ownership of content, cancellation and dispute handling.
CONTRACT
Privacy / Confidentiality Terms
WHY YOU NEED IT NOW
LearnReach may receive client and prospective learner information while handling enquiries and campaigns.
WHAT IT MUST SPECIFICALLY COVER
Permitted use of data, access controls, confidentiality, secure storage, retention/deletion, consent and responsibilities for data handling.
FOUNDER WORKBOOK · Section 3: Legal Structure Plan
17

## Slide 21
You're Ready to Launch
Revisit this deck as your venture evolves — sales & marketing, operations, and legal foundations all shift as you learn.
FOUNDER WORKBOOK · STARTUP OPERATIONS & LAUNCH PLAN